## User Stories
ID | Importance | Story Title | Depends On | Points | Priority | As a/an [user type] | I want [functionality] | So that [value] | NFR | Definition of Done | Epic ID | Notes | Status
Account details
S1 | Major | Login | User has account | 1 | High | Account user | to log in | I can save my progress |  | When in lobby |  |  | Open
S2 | Major | Log out | User has account | 1 | High | Account user | to log out | i can save my progress |  | When I am at the log in page |  |  | Open
S3 | Major | Create account | User doesn't have account | 2 | High | Any User | to create an account | I can track game history and keep money |  | When at login page |  |  | Open
Table Actions
S4 | Major | Create Table | User is in lobby | 5 | High | Account user | to create a table | I can host a table |  | I become the host of a table and get to set the values | 1 | Updates lobby as well | Open
S5 | Major | Set payout ratio | User is creator of table | 1 | Medium | Table creator | set the payout ratio | the stakes are either 1 to 1 or 3 to 2 |  | when I recieve payment on my wager | 1 |  | Open
S6 | Major | Set betting increments | User is creator of table | 1 | Medium | Table creator | manage how much a player can bet | there is a limit in gameplay |  | when I place a bet within those increments | 1 |  | Open
S7 | Major | Set minimum bet | User is creator of table | 1 | Medium | Table creator | set the minimum betting value | Players cannot bet too low |  | when I cant bet below that value | 1 |  | Open
S8 | Major | Set maximum bet | User is creator of table | 1 | Medium | Table creator | limit the maximum betting value | Players are cannot bet too high |  | when I can't bet above that value | 1 |  | Open
S9 | Major | Set amount of seats | User is creator of table | 1 | Medium | Table creator | to set the number of seats at a table | I can set the amount of users in a game |  | when the table is created | 1 |  | Open
S10 | Minor | View Table info | User is in lobby | 3 | Medium | Any User | to see table players (usernames), payout, seats left | i can decide if i want to join the table |  | table info is shown |  |  | Open
S11 | Minor | Join table | User is in lobby | 2 | High | Any User | to join a black jack table | I can play black jack games |  | when Ive joined the table |  |  | Open
S12 | Minor | Leave table | user is at a table | 2 | medium | Any User | to leave a table | i can do something else besides blackjack |  | left table and am back in the lobby |  |  | Open
S13 | Minor | Join game | User is at a table | 2 | High | Any User | to join the next game at the table | I can play the next game of black jack |  | when I get dealt a hand in the next game |  |  | Open
S14 | Minor | Stand | User is playing a game | 1 | High | Any User | to stand (stop recieving cards) | I can stop getting cards |  | when I stop getting cards and my turn is over |  |  | Open
S15 | Minor | Hit | User is playing a game | 1 | High | Any User | to hit (be given another card) | I can get another card |  | when I get another card and my turn continues |  |  | Open
S16 | Minor | Change Ace Value | User has ace | 1 | Medium | Any user | to change the value of my ace | I have a better chance of winning |  | when the value in the players hand reflects the correct sum with the changed ace value |  | All Aces in that players hand have to be the same value | Open
S17 | Minor | Open chat (table) | User is at a table | 1 | Low | Any User | to open chatbox | i can see messages |  | When I see the chat window pop up on the side of the screen |  |  | Open
S18 | Minor | Send a chat (table) | User is at a table | 2 | Low | Account user | to send a message to chatbox | i can talk to other players at table |  | When the chat updates and I see the message I sent so that other players can see |  |  | Open
S19 | Minor | Close chat (table) | User is at a table | 1 | Low | Any User | to close chatbox | i can ignore messages |  | when the chat window is no longer on the screen |  |  | Open
Misc. Lobby Actions
S20 | Minor | View game history | User has account | 2 | Low | Account user | to view personal stats | I can see my wins and losses |  | when I see my winnings and my game history |  |  | Open
S21 | Minor | Request chips | User has lost all chips | 1 | High | Any User | to be able to get more chips when I run out | I can keep playing games |  | when I have more chips in my bank |  |  | Open
S22 | Minor | View tutorial | New user | 1 | Low | New User | to viewa tutorial | I know how to play the game |  | when the tutorial wiki page shows up |  |  | Open
S23 | Minor | Send email to admin | Any user | 5 | Low | Any User | to send an admin an email | i can offer suggestions/ask questions |  | when the email is sent |  | client wants this to open 3rd party email app | Open
Admin Only Actions
S24 | Major | Reset Password | User has account | 2 | Low | Account user | to change password | I can access the account |  | when i can login with the new password |  |  | Open
S25 | Major | Modify Profile | User has account | 2 | Low | Account user | to change my profile | I can change my information |  | when the profile reflects the changes made |  |  | Open

## Tasks
ID | Task Title | Task Description | Story ID

## Epics
ID | Epic Title | Description