## User_Stories
ID | Importance | Story Title | Depends On | Points | Priority | As a/an [user type] | I want [functionality] | So that [value] | NFR | Definition of Done | Epic ID | Notes | Status
Account details
S1 | Major | Login | User has account | 2 | High | Account user | to log in | I can save my progress |  | When in lobby |  |  | Open
S2 | Major | Log out | User has account | 1 | High | Account user | to log out | i can save my progress |  | When I am at the log in page |  |  | Open
S3 | Major | Create account | User doesn't have account | 2 | High | Any user | to create an account | I can track game history and keep money |  | When at login page |  |  | Open
S4 | Major | View Friends List | User has an account | 1 | High | Account user | to view my friends list | I can see my friends on the app |  | When I can see a list with my friends on it |  |  | Open
S5 | Major | Add Friend | Target account is not already a friend of the user | 1 | High | Account user | to add a friend to my friends list | I can add a new friend to my friends list |  | When I see the newly added friend in the list |  |  | Open
S6 | Major | Remove Friend | Target is in user's friend list | 1 | High | Account user | to remove a friend from my friends list | I can remove friends from the list |  | When I no longer see that friend in the list |  |  | Open
S7 | Major | Play as guest | User wants to play anonymously | 2 | High | Any user | to play anonymously as a guest | I can play without having to create an accout |  | When I'm in a lobby as a guest user |  |  | Open
Table Actions
S8 | Major | Create Table | User is in lobby | 2 | High | Account user | to create a table | I can create a new table with set attributes |  | I become the host of a table and get to set the values |  | "Table creator" is synonymous with "host" | Open
S9 | Minor | View Table info (individual table) | User is in lobby | 2 | Medium | Any User | to see table players (usernames), payout, seats left | i can decide if i want to join the table |  | table info is shown |  |  | Open
S10 | Minor | Join table | User is in lobby | 2 | High | Any User | to join a black jack table | I can play black jack games |  | when Ive joined the table |  |  | Open
S11 | Minor | Leave table | user is at a table | 2 | Medium | Any User | to leave a table | i can do something else besides blackjack |  | left table and am back in the lobby |  |  | Open
S12 | Minor | Join game | User is at a table | 2 | High | Any User | to join the next game at the table | I can play the next game of black jack |  | when I get dealt a hand in the next game |  |  | Open
S15 | Minor | Change Ace Value | User has ace | 1 | Medium | Any user | to change the value of my ace | I have a better chance of winning |  | when the value in the players hand reflects the correct sum with the changed ace value |  | All Aces in that players hand have to be the same value | Open
S17 | Minor | Send a chat (table) | User is at a table | 2 | Low | Account user | to send a message to chatbox | i can talk to other players at table |  | When the chat updates and I see the message I sent so that other players can see |  | absorbs S16 and S18 | Open
S26 | Major | Play Blackjack | User is at table | 3 | High | Any User | to play blackjack | I can play blackjack games |  | when I’m playing blackjack at a table |  | replaces S13 and S14 | Open
Misc. Lobby Actions
S19 | Minor | View game history | User has account | 2 | Low | Account user | to view personal stats | I can see my wins and losses |  | when I see my winnings and my game history |  |  | Open
S20 | Major | Request/buy chips (not actually "buying them" | User has 0$ worth of chips | 2 | High | Any User | to be able to get more chips when I run out | I can keep playing games |  | when I have more chips in my bank |  |  | Open
S21 | Minor | View tutorial | Any user | 1 | High | New User | to viewa tutorial | I know how to play the game |  | when the tutorial wiki page shows up |  |  | Open
S22 | Minor | Send message to admin | Any user | 2 | Low | Any User | to send an admin an email | I can offer suggestions/ask questions |  | when the email is sent |  | client wants this to open 3rd party email app | Open
S23 | Minor | Send message to friends | User has friends in friends list | 2 | Medium | Account user | to send messages to friends | I can talk with my friends |  | when the message I send is received by that friend |  | should operate like email (have to open inbox) | Open
Admin Only Actions
S24 | Major | Reset Password | User has account | 2 | Low | Admin Account | to change password | I can access the account |  | when i can login with the new password |  |  | Open
S25 | Major | Modify Profile | User is Admin | 2 | Low | Admin Account | to change a users's profile | I can change my information |  | when the profile reflects the changes made |  |  | Open
Total |  |  |  | 39

## Tasks
ID | Task Title | Task Description | Story ID

## Epics
ID | Epic Title | Description