## User_Stories
ID	Importance	Story Title	Depends On	Points	Priority	As a/an [user type]	I want [functionality]	So that [value]	NFR	Definition of Done	Epic ID	Notes	Status
	Account details
S1	Major	Login	User has account	2	High	Account user	to log in	I can save my progress		When in lobby			Open
S2	Major	Log out	User has account	1	High	Account user	to log out	i can save my progress		When I am at the log in page			Open
S3	Major	Create account	User doesn't have account	2	High	Any user	to create an account	I can track game history and keep money		When at login page			Open
S4	Major	View Friends List	User has an account	1	High	Account user	to view my friends list	I can see my friends on the app		When I can see a list with my friends on it			Open
S5	Major	Add Friend	Target account is not already a friend of the user	1	High	Account user	to add a friend to my friends list	I can add a new friend to my friends list		When I see the newly added friend in the list			Open
S6	Major	Remove Friend	Target is in user's friend list	1	High	Account user	to remove a friend from my friends list	I can remove friends from the list		When I no longer see that friend in the list			Open
S7	Major	Play as guest	User wants to play anonymously	2	High	Any user	to play anonymously as a guest	I can play without having to create an accout		When I'm in a lobby as a guest user			Open
	Table Actions
S8	Major	Create Table	User is in lobby	2	High	Account user	to create a table	I can create a new table with set attributes		I become the host of a table and get to set the values		"Table creator" is synonymous with "host"	Open
S9	Minor	View Table info (individual table)	User is in lobby	2	Medium	Any User	to see table players (usernames), payout, seats left	i can decide if i want to join the table		table info is shown			Open
S10	Minor	Join table	User is in lobby	2	High	Any User	to join a black jack table	I can play black jack games		when Ive joined the table			Open
S11	Minor	Leave table	user is at a table	2	Medium	Any User	to leave a table	i can do something else besides blackjack		left table and am back in the lobby			Open
S12	Minor	Join game	User is at a table	2	High	Any User	to join the next game at the table	I can play the next game of black jack		when I get dealt a hand in the next game			Open
S13	Minor	Stand	User is playing a game	1	High	Any User	to stand (stop recieving cards)	I can stop getting cards		when I stop getting cards and my turn is over			Open
S14	Minor	Hit	User is playing a game	1	High	Any User	to hit (be given another card)	I can get another card		when I get another card and my turn continues			Open
S15	Minor	Change Ace Value	User has ace	1	Medium	Any user	to change the value of my ace	I have a better chance of winning		when the value in the players hand reflects the correct sum with the changed ace value		All Aces in that players hand have to be the same value	Open
S16	Minor	Open chat (table)	User is at a table	1	Low	Any User	to open chatbox	i can see messages		When I see the chat window pop up on the side of the screen			Open
S17	Minor	Send a chat (table)	User is at a table	2	Low	Account user	to send a message to chatbox	i can talk to other players at table		When the chat updates and I see the message I sent so that other players can see			Open
S18	Minor	Close chat (table)	User is at a table	1	Low	Any User	to close chatbox	i can ignore messages		when the chat window is no longer on the screen			Open
	Misc. Lobby Actions
S19	Minor	View game history	User has account	2	Low	Account user	to view personal stats	I can see my wins and losses		when I see my winnings and my game history			Open
S20	Major	Request/buy chips (not actually "buying them"	User has 0$ worth of chips	2	High	Any User	to be able to get more chips when I run out	I can keep playing games		when I have more chips in my bank			Open
S21	Minor	View tutorial	Any user	1	High	New User	to viewa tutorial	I know how to play the game		when the tutorial wiki page shows up			Open
S22	Minor	Send message to admin	Any user	2	Low	Any User	to send an admin an email	I can offer suggestions/ask questions		when the email is sent		client wants this to open 3rd party email app	Open
	Minor	Send message to friends	User has friends in friends list	2	Medium	Account user	to send messages to friends	I can talk with my friends		when the message I send is received by that friend		should operate like email (have to open inbox)	Open
	Admin Only Actions
S23	Major	Reset Password	User has account	2	Low	Admin Account	to change password	I can access the account		when i can login with the new password			Open
S24	Major	Modify Profile	User is Admin	2	Low	Admin Account	to change a users's profile	I can change my information		when the profile reflects the changes made			Open

Total				40

## Tasks
ID	Task Title	Task Description	Story ID

## Epics
ID	Epic Title	Description